## Sheet1
|  | 18th - 24th Nov | 25th Nov - 1st Dec | 2nd - 8th Dec | 9th - 15th Dec | 16th - 22nd Dec | 23rd - 29th Dec | 30th Dec - 5th Jan | 6th -12th Jan | 13th - 19th Jan | 20th - 26th Jan
Planning | Game Loop and Features
| GDD | [10 empty] | Zoe
| TDD | [10 empty] | Ryan M
Map | Setup Room Class | [10 empty] | Liam D
| Setup Map Class | [10 empty] | Ryan F
| Load Rooms from Folder | [10 empty] | Liam N
| Randomly Generate | [10 empty] | Everyone
Collision
Mini Map | Generate Mini Map
Update Map on Room Change
Render Mini Map
Collision | Setup Class
Setup Rectangle Class
Projectile | Setup Class
Player | Setup Class
Controller Movement
Shoot in Direction Facing
Items | Setup Class
On Collision With Player Act
Enemy | Setup Enemy Class
Demons | Setup Demon Class
Movement
Shooting
Ghosts | Setup Ghost Class
Random Movement
Pick Random Object
Move Object to Unblocked Door
Axe Psycho | Setup Axe Psycho Class
Audio and Visual Signs Before Appearance
Movement
Hits if in Range
Runs Away at Low Health
Powerups | Unlock Player Ability
UI | Setup Scene Manager Class
Menu Screen
Game Screen
Shop Screen
Game Over Screen
Gameplay | Death on Low Health
Reset Game
Win on Exit
Shop | Powerup Display
Menu Selector
Buy Powerup
Activate Powerup
Testing